## burnUp
Sprint ID	SP Scope	Sprint end-date	Committed SP	Burned SP	Total SP burned	Forecast completion	Forecast high	Forecast low
1	48	17-Feb S171	8	8	8	8	8	8		rubberDucky MD estimate		120
2	48	24-Feb S172	8	2	10	10	10	10		MD/sprint		10	ex. 2 ppl doing committing to rubberDucky
3	96	02-Mar S173	8	6	16	18	20	17		Avg velocity		8.9	Last 7 sprints
4	62	09-Mar S174	12	8	24	27	30	24		Avg rubberDucky velocity		8.43	Last 7 sprints
5	64	16-Mar S175	9	3	27	35	40	31		StdDev velocity		1.5	>= 1 indicates a relatively high variation and <1 can be considered low. This indicates how your data spreads out
6	74	23-Mar S176	8	8	35	44	50	38		Sprints to complete		12
7	75	30-Mar S177	7	4	39	52	60	45		SP per quarter		106	4 weeks, 3 months
8	81	06-Apr S178	10	8	47	61	70	51
9	83	13-Apr S179	12	8	55	69	80	58	`
10	83	20-Apr S180	9	9	64	77	90	65		Sprint name	All committed SP	Actual SP	rubberDucky SP	rubberDucky actual SP
11	93	27-Apr S181	10	8	72	86	100	72		S159	6	6	no rubberDucky increment yet
12	99	04-May S182	13	6	78	94	110	79		S160	10	13
13	99	11-May S183	17	13	91	103	120	86		S161	12	15
14	106	18-May S184	13	7	98	111	129	93		S162	14	5
15	106	25-May S185	10	8	106	120	139	100		S163	12	7
										S164	11	11
										S165	7	5
										S166	10	5
										S167	18	15
										S168	14	8
										S169	10	15
										S170	12	12
										S171	12	12	8	8
										S172	10	2	8	2
										S173	11	9	8	6
										S174	12	8	12	8
										S175	17	5	9	3
										S176	11	11	8	8
										S177	10	7	7	4
										S178	12	8	10	8
										S179	15	8	12	8
										S180	16	10	9	9
										S181	17	10	10	8
										S182	13	8	13	6
										S183	19	13	17	13
										S184	15	9	13	7
										S185	22	10	10	8
										S186
										S187
										S188
rubberDucky burn-up chart (delivery time forecast)
Iterations (sprints)